## Gantt
SMART CONTROL TOWER ¦ PHASE 1 → PHASE 2 GANTT
Phase 1: 26 Sep–3 Oct ¦ Phase 2: from 5 Oct, conditional on October data receipt and requirement verification
Phase / work item | Discussion / output | Owner | Status | Start | Finish | 2026-09-26 | 2026-09-27 | 2026-09-28 | 2026-09-29 | 2026-09-30 | 2026-10-01 | 2026-10-02 | 2026-10-03 | 2026-10-04 | 2026-10-05 | 2026-10-06 | 2026-10-07 | 2026-10-08 | 2026-10-09 | 2026-10-10 | 2026-10-11 | 2026-10-12 | 2026-10-13 | 2026-10-14 | 2026-10-15 | 2026-10-16
PHASE 1 ¦ Discussion + Ksan plant visit | Visit and capture process needs | TBD | COMPLETE | 2026-09-26 | 2026-09-29 | bar: 2026-09-26 to 2026-09-29
PHASE 1 ¦ HTML pilot + AI | Build and review local prototype | TBD | COMPLETE | 2026-09-29 | 2026-10-03 | bar: 2026-09-29 to 2026-10-03
PHASE 1 ¦ October data verification | Receive October data; Ashutosh + Abhishek verify fields and requirements | Ashutosh + Abhishek | PENDING DATA | 2026-10-05 | 2026-10-07 | bar: 2026-10-05 to 2026-10-07
PHASE 2 ¦ Choose stack + LLM provider | Confirm app stack; coordinate with LLM provider | TBD | GATED | 2026-10-05 | 2026-10-07 | bar: 2026-10-05 to 2026-10-07
PHASE 2 ¦ Private server option | Check private-network deployment option | TBD | GATED | 2026-10-05 | 2026-10-07 | bar: 2026-10-05 to 2026-10-07
PHASE 2 ¦ DFOS data automation | Check for internal DFOS API to replace manual updates | TBD | GATED | 2026-10-05 | 2026-10-09 | bar: 2026-10-05 to 2026-10-09
PHASE 2 ¦ Build + validate pilot | Fresh daily data, validated API, remarks flow, selected LLM | TBD | PLANNED* | 2026-10-08 | 2026-10-14 | bar: 2026-10-08 to 2026-10-14
PHASE 2 ¦ Private-network pilot review | Deploy option and user review | TBD | PLANNED* | 2026-10-15 | 2026-10-16 | bar: 2026-10-15 to 2026-10-16
*Phase 2 dates are tentative: work starts after October data arrives and Ashutosh + Abhishek verify requirements.