## Overview
SMART CONTROL TOWER ¦ TWO-WEEK DELIVERY PLAN
Planning window: 05–16 Oct 2026 ¦ 10 working days ¦ Draft plan; October source data pending from Ashutosh
GOAL & PHASES
Overall goal | Move from the current HTML + AI pilot to a lightweight, validated FastAPI application reachable only on the approved private network.
Phase 1 ¦ Oct 5–7 | Review and accept the HTML prototype with AI, structured responses, provider fallback, and clear data/privacy boundaries.
Phase 2 ¦ Oct 7–16 | Deliver FastAPI Lite with validated APIs, daily fresh-data refresh, remarks receive/review, private-network deployment, and UAT.
Critical dependency | October production + downtime data and remarks from Ashutosh. Target handoff: Oct 6; mapping approval: Oct 8.
API readiness | Groq live check passed with openai/gpt-oss-120b. OpenAI currently has no credits; Mistral returned a rate-limit error.
MILESTONES
ID | Milestone | Target date | Exit evidence | Owner | Status | Dependency
M1 | Phase 1 pilot accepted | 2026-10-07 | HTML + AI review complete | User | Planned | T1–T2
M2 | October data mapping approved | 2026-10-08 | Fields, dates, remarks, cadence confirmed | Ashutosh + User | Blocked - data | D1
M3 | Validated API endpoints ready | 2026-10-09 | Health + data routes pass schema checks | Developer | Planned | T3–T4
M4 | Daily refresh + remarks integrated | 2026-10-13 | October sample loads and remarks can be reviewed | Developer + User | Planned | D1, T5–T6
M5 | Private-network pilot reachable | 2026-10-14 | Approved internal client reaches API | Developer + IT | Planned | M3–M4
M6 | Phase 2 go/no-go | 2026-10-16 | UAT decision and next actions recorded | User | Planned | T8
DECISION / ASSUMPTIONS
• Schedule uses weekdays only. October data target is Oct 1 onward, including source field definitions and remarks.
• If Ashutosh’s data arrives late, continue API scaffolding with current Sep/Mar samples but move fresh-data UAT; do not sign off freshness without October data.
• Private-network host, access method, API authentication, and IT owner must be confirmed by Oct 9 to protect the Oct 14 deployment milestone.

## Gantt & Workplan
WORKPLAN & GANTT ¦ 05–16 OCT 2026
Bars show planned working days. Update Start/Finish or Status to maintain the plan; October data from Ashutosh is the critical path.
Teal = Phase 1 ¦ Navy = Phase 2 ¦ Gold = data dependency ¦ Green = milestone | [10 empty] | TWO-WEEK GANTT • WEEKDAYS
ID | Phase | Workstream | Goal / deliverable | Owner | Status | Start | Finish | Workdays | Predecessor / dependency | Files / evidence | 2026-10-05 | 2026-10-06 | 2026-10-07 | 2026-10-08 | 2026-10-09 | 2026-10-12 | 2026-10-13 | 2026-10-14 | 2026-10-15 | 2026-10-16
T1 | Phase 1 | Prototype review and scope freeze | Confirm current HTML dashboard, AI flow, data boundaries, and Phase 1 acceptance checklist. | Developer + User | Review pending | 2026-10-05 | 2026-10-05 |  | prototype.html; ai_local_server.py | Existing pilot; review/sign-off remains
T2 | Phase 1 | AI response and fallback handoff | Review structured Markdown replies, provider attribution, local key handling, and fallback UX. | Developer | Ready for review | 2026-10-05 | 2026-10-06 |  | prototype.html; ai_local_server.py; test_ai_pilot.py | Groq live check passed; OpenAI credits/Mistral limits noted
M1 | Milestone | Phase 1 pilot accepted | HTML prototype with AI reviewed and acceptance notes captured. | User | Planned | 2026-10-07 | 2026-10-07 |  | prototype.html | Phase 1 exit gate
D1 | Data | October source-data handoff | Receive October production and downtime daily data, field definitions, and remarks from Ashutosh. | Ashutosh | Blocked - data | 2026-10-05 | 2026-10-06 |  | October DFOS + downtime files; remarks | Critical dependency; pending from Ashutosh
T3 | Phase 2 | API contract and data schemas | Define validated request/response schemas for production, downtime, daily refresh, and remarks. | Developer + User | Planned | 2026-10-07 | 2026-10-08 |  | app/schemas.py; API contract | Can draft with current sample files; confirm after D1
M2 | Milestone | October data mapping approved | Confirm date, machine, model, downtime, reason, and remarks fields and refresh cadence. | Ashutosh + User | Blocked - data | 2026-10-08 | 2026-10-08 |  | Data dictionary / mapping | Must unblock ingestion and remarks review
T4 | Phase 2 | FastAPI Lite service foundation | Create FastAPI app, health/status route, validated API routes, configuration, and private-key loading. | Developer | Planned | 2026-10-08 | 2026-10-09 |  | app/main.py; app/api/routes.py; .env.example | FastAPI package/runtime availability
M3 | Milestone | Validated API endpoints ready | Health and data routes return schema-validated responses with clear errors. | Developer | Planned | 2026-10-09 | 2026-10-09 |  | app/main.py; app/schemas.py | API smoke check
T5 | Phase 2 | Daily data refresh and validation | Load fresh October files, validate required fields/freshness, and surface missing or duplicate data. | Developer | Planned | 2026-10-09 | 2026-10-13 |  | app/services/data_refresh.py | October sample and refresh cadence from Ashutosh
T6 | Phase 2 | Remarks receive and review flow | Preserve incoming remarks, link to date/machine where possible, and expose review status through the API. | Developer + Ashutosh | Planned | 2026-10-12 | 2026-10-13 |  | app/services/remarks.py; app/schemas.py | Remarks fields and ownership confirmation
M4 | Milestone | Daily refresh and remarks integrated | Fresh-data endpoint and remarks review path work against supplied October sample. | Developer + User | Planned | 2026-10-13 | 2026-10-13 |  | API + sample data | Data dependency must be received
T7 | Phase 2 | Private-network deployment | Run service on approved internal host, restrict access to private network, and validate API credentials/config. | Developer + IT | Planned | 2026-10-14 | 2026-10-14 |  | deployment config; README.md | Internal host/network access
M5 | Milestone | Private-network pilot reachable | Health/data endpoints reachable from an approved internal client only. | Developer + IT | Planned | 2026-10-14 | 2026-10-14 |  | Deployment URL / runbook | Network allowlist and credentials
T8 | Phase 2 | Integration UAT and fixes | Verify freshness, schema validation, remarks visibility, and fallback/AI behavior with users. | User + Developer | Planned | 2026-10-15 | 2026-10-15 |  | UAT checklist; test_ai_pilot.py | October data and internal access
M6 | Milestone | Phase 2 go/no-go | Record acceptance, open issues, owner, and next release decision. | User | Planned | 2026-10-16 | 2026-10-16 |  | Sign-off notes | UAT approval
Formulas:
Workdays = NETWORKDAYS([Start],[Finish])

## Dependencies
DATA & DELIVERY DEPENDENCIES
Resolve critical inputs early; status is editable. No October freshness sign-off without the October source files.
ID | Dependency | Owner | Needed by | Status | Impact if late | Mitigation / decision
D1 | October production + downtime data (daily, Oct 1 onward), remarks, and field definitions | Ashutosh | 2026-10-06 | Pending | Blocks production-ready daily refresh, remarks linkage, and freshness UAT. | Build schemas with Sep/Mar samples; keep UAT blocked until October sample arrives.
D2 | Refresh source location, delivery cadence, and named data owner | Ashutosh + User | 2026-10-08 | Pending | Cannot automate or verify daily freshness without a stable source/cadence. | Confirm folder/API drop path and expected update time during mapping.
D3 | Private-network host, access route, and IT/network contact | IT + User | 2026-10-09 | Pending | Oct 14 deployment target may slip. | Select an approved internal host and confirm firewall/allowlist early.
D4 | Validated AI provider key/model for pilot service | User + Developer | 2026-10-09 | In progress | AI feature cannot be accepted if no provider answers. | Groq smoke test passed; OpenAI reports no credits and Mistral rate limit exceeded.

## File Register
FILE & EVIDENCE REGISTER
Existing files are separated from Phase 2 targets. Planned paths are proposed locations, not files already present.
File / artifact | State | Phase | Purpose / evidence | Owner | Dependency / note
prototype.html | Exists | Phase 1 | Dashboard prototype and AI assistant interface | Developer | Local pilot; structured Markdown render
ai_local_server.py | Exists | Phase 1 | Loopback-only AI bridge, provider fallback, dashboard summary API | Developer | Local-only; Phase 2 moves API into FastAPI
test_ai_pilot.py | Exists | Phase 1 | Routing smoke tests and per-provider live checks | Developer | Groq live check passed; provider quotas differ
.env.example | Exists | Phase 1/2 | Document required keys/config without secrets | Developer | Never commit .env
data/DFOS Dashboard (1).xlsx | Exists - sample | Data | September production dashboard source | User | Not the pending October fresh-data source
data/Fw__Downtime_data_from_Nov'25_to_Mar'26/Downtime_Report_Mar'26( 1 to 30).xlsx | Exists - sample | Data | March detailed downtime and remarks sample | User | Use for schema development; not October freshness proof
app/main.py | Planned | Phase 2 | FastAPI app entry point, health route, local/private bind config | Developer | Create after API contract
app/api/routes.py | Planned | Phase 2 | Validated production, downtime, refresh, and remarks endpoints | Developer | Depends on approved schemas
app/schemas.py | Planned | Phase 2 | Pydantic request/response and source row validation models | Developer | Depends on Ashutosh field map
app/services/data_refresh.py | Planned | Phase 2 | Daily source ingestion, freshness checks, duplicate/missing field validation | Developer | Depends on October data location/cadence
app/services/remarks.py | Planned | Phase 2 | Capture, link, and review remarks with status | Developer + Ashutosh | Confirm fields and process with Ashutosh
README.md | Planned | Phase 2 | Private-network setup, API usage, refresh runbook, troubleshooting | Developer | Needed for handoff